Reply Slip

To:	Ms. Winnie Lo 								(Fax no: 2845 0387)

Assistant Director of External Affairs

- Project schedule for the Professional Development Programme 2002 – 2004

In-bound PDP

| No. | Date (originally proposed) | No. of PRC lawyers participating In-bound PDP | Provinces / cities selected for In-bound PDP (subject to confirmation) | Completion Date or Re-arranged Date | I would like to take one lawyer from the following provinces/cities (you may take more than one) |
| --- | --- | --- | --- | --- | --- |
| 1 | Nov 2002 | 12 | - Anhui | - November 2002 (completed) | - N/A |
| 2 | Dec 2002 | 12 | Hubei | February 2003 (completed) | N/A |
| 3 | Mar 2003 | 12 | Shandong | August 2003 (completed) | N/A |
| 4 | April 2003 | 11 | Guangdong/ Guangzhou | July 2003 (completed) | N/A |
| 5 | May 2003 | 11 | Hunan | February 2004 | N/A |
| 6 | July 2003 | 12 | - Zhejiang (Ningbo & Hangzhou included) | - March 2004 |  |
| 7 | Jan 2003 | 12 | Beijing | April 2004 |  |
| 8 | Aug 2003 | 12 | Jiangsu | May 2004 |  |
| 9 | Sep 2003 | 12 | Jilin | June 2004 |  |
| 10 | Oct 2003 | 12 | Shanghai | July 2004 |  |
| 11 | Nov 2003 | 12 | Xinjiang | August 2004 |  |
| 12 | Dec 2003 | 12 | Liaoning (Dalian included) | September 2004 |  |

Remarks:

A total of 192 Mainland lawyers are expected to participate in the In-bound Professional Development Programme during the period between Nov 2002 and Mar 2004. However, due to SARS outbreak in early 2003 and other unexpected mainland activities arising in the same period, the schedule has to be revised as above. The number of participants has been reduced from 192 to 142.