Reply Slip

To:	Ms. Winnie Lo 	(Fax no: 2845 0387)

Assistant Director of External Affairs

The Law Society of Hong Kong

Project schedule for the Professional Development Programme 2002 - 2004

In-bound PDP

| No. | Date (originally proposed) | No. of PRC lawyers participating In-bound PDP | Provinces / cities selected for In-bound PDP (subject to confirmation) | Completion Date or Re-arranged Date | I would like to take one lawyer from the following provinces/cities (you may take more than one) |
| --- | --- | --- | --- | --- | --- |
| 1 | Nov 2002 | 12 | Anhui | - November 2002 (completed) | - N/A |
| 2 | Dec 2002 | 12 | Hubei | February 2003 (completed) | N/A |
| 3 | Mar 2003 | 12 | Shandong | August 2003 (completed) | N/A |
| 4 | April 2003 | 11 | Guangdong/ Guangzhou | July 2003 (completed) | N/A |
| 5 | May 2003 | 11 | Hunan | February 2004 | N/A |
| 6 | July 2003 | 12 | - Zhejiang (Ningbo & Hangzhou included) | - March 2004 | - N/A |
| 7 | Jan 2003 | 12 | Beijing | April 2004 |  |
| 8 | Aug 2003 | 12 | Jiangsu | May 2004 |  |
| 9 | Sep 2003 | 12 | Jilin | June 2004 |  |
| 10 | Oct 2003 | 12 | Shanghai | July 2004 |  |
| 11 | Nov 2003 | 12 | Liaoning (Dalian included) | August 2004 (revised) |  |
| 12 | Dec 2003 | 12 | Xinjiang | September 2004 (revised) |  |