- Project schedule for the Professional Development Programme 2002 - 2004

- Out-bound PDP

| No. | Date (originally proposed) | No. of HK solicitors participating out-bound PDP | Provinces / cities selected for In-bound PDP (subject to confirmation) | Completion Date or Re-arranged Date |
| --- | --- | --- | --- | --- |
| 1 | Nov 2002 | 6 | - Sichuan | - 23Aug - 6 Sep 03 (completed) |
| 2 | Dec 2002 | 6 | Fujian/Fuzhou | 23 Aug – 6 Sep 04 (Postponed) |
| 3 | Jan 2003 | 6 | Shanxi | 23 Aug – 6 Sep 04 |
| 4 | Mar 2003 | 6 | Anhui | 4 – 17 April 2004 (Vacant) |
| 5 | April 2003 | 6 | Hubei | 23 Aug – 6 Sep 04 (Postponed) |
| 6 | May 2003 | 6 | Beijing | 23 Aug – 6 Sep 04 |
| 7 | June 2003 | 6 | Shangdong | 4 – 17 April 2004 (Vacant) |
| 8 | July 2003 | 6 | - Guangdong/Guangzhou | - 4 – 17 April 2004 (FULL) |
| 9 | Aug 2003 | 6 | Hunan | 23 Aug – 6 Sep 04 (Postponed) |
| 10 | Sept 2003 | 6 | Ningbo | 23 Aug – 6 Sep 04 |